## Sheet1
ITSC-3155 Software Engineering
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
Menu API | High | 8 | As restaurant staff, I want API endpoints to create, retrieve, update, and delete menu items so that customers always have an up-to-date menu. | Sprint 1 | 1
Menu Category API | High | 5 | As a customer, I want to retrieve menu items by category (spicy, kids, vegetarian, low fat, etc.) so that I can easily find meals that fit my preferences. | Sprint 1 | 1
Menu Item Details API | High | 3 | As a customer, I want to view a menu item’s ingredients, price, calories, and category so that I can make informed ordering decisions. | Sprint 1 | 1
Guest Order API | High | 8 | As a customer, I want to place an order without creating an account so that I can order food quickly. | Sprint 2 | 2
Customer Information API | High | 3 | As a customer, I want to provide my name, phone number, and delivery address with each order so that my food can be delivered correctly. | Sprint 2 | 2
Delivery/Pickup API | High | 3 | As a customer, I want to choose between delivery and takeout when placing my order. | Sprint 2 | 2
Payment API | High | 8 | As a customer, I want to pay using different payment methods so that I can complete my purchase securely. | Sprint 2 | 2
Order Tracking Number API | High | 5 | As a customer, I want to receive a tracking number after placing my order so that I can track it later. | Sprint 2 | 2
Order Status API | High | 5 | As a customer, I want to retrieve my order status using my tracking number so that I know the progress of my order. | Sprint 3 | 3
Staff Order Management API | High | 8 | As restaurant staff, I want API endpoints to view and manage customer orders so that orders can be processed efficiently. | Sprint 3 | 3
Chef Kitchen API | High | 5 | As a chef, I want to retrieve pending orders so that I know which meals need to be prepared. | Sprint 3 | 3
Update Order Status API | High | 5 | As restaurant staff, I want to update an order’s status (Received, Preparing, Ready, Out for Delivery, Completed) so that customers receive accurate updates. | Sprint 3 | 3
Reviews & Ratings API | Medium | 5 | As a customer, I want to submit a rating and review after my order is completed so that I can provide feedback. | Sprint 4 | 4
Promo Code API | Medium | 5 | As restaurant staff, I want to create and manage promotional codes so that customers can receive discounts. | Sprint 4 | 4
Sales Analytics API | Medium | 8 | As the restaurant owner, I want API endpoints that provide sales trends and customer ordering data so that I can make informed business decisions. | Sprint 4 | 4
Customer Preference Analytics API | Medium | 5 | As the restaurant owner, I want to retrieve reports on popular menu items and customer preferences so that I can improve the menu. | Sprint 5 | 5
Swagger API Documentation | High | 3 | As a developer, I want all API endpoints documented in Swagger UI so that the API can be easily tested and demonstrated. | Sprint 5 | 5
Technical Documentation | Low | 3 | As a developer, I want technical documentation for the API so that future developers can maintain and extend the system. | Sprint 5 | 5